## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Cleanup Project | 3 | 3 | 5 | 0 | A. Walliser
Add some UI windows to group, list and home fragment | 5 | 4 | 4 | 0 | A.Walliser
Switch localsave method to Gson | 4 | 9 | 9 | 0 | C.Wagner
Switch localsave method to Gson | 0 | 9 | 9 | 0 | A. Walliser
Get ip-adress of server during buildtime | 2 | 2 | 2 | 0 | C.Wagner
Write config file with currently used shoppinglist | 1 | 1 | 1 | 0 | A. Walliser