## Tabelle1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Read items locally from json format | 2 | 2 | 2 | 0 | Wagner C.
Impliment a login window | 4 | 3 | 3 | 0 | Walliser A.
Save items locally in json format | 4 | 6 | 6.5 | 0 | Wagner C.