## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Implement clientsite groupfeature | 6 | 6 | 5 | 0 | Walliser A.
Fix a bug that causes the app to crach on api 21 | 4 | 6 | 10 | 0 | Walliser A.
Finalize localsave of shoppinglists and itemlists | 3 | 3 | 5 | 0 | Wagner C.
Fix a bug that casues the the "gekauft" category to close when adding a new item | 4 | 4 | 4 | 0 | Walliser A.
Impliment multiple list feature clientsite | 4 | 4 | 4 | 0 | Walliser A.