## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Put Postgres database on AWS-Server | 2 | 4 | 2 | 2 | C. Wagner
Put Asp .net Application Server on AWS-Server | 2 | 4.5 | 1.5 | 3 | C. Wagner
Integrate login feature into the client | 3 | 3 | 3 | 0 | C. Wagner
Make application server accessable from devices in the same network | 6 | 6 | 6 | 0 | C. Wagner
Make register Activity | 6 | 4 | 4 | 0 | A. Walliser