## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Implemented invations clientside | 4 | 3 | 3 | 0 | Wagner C.
Fixing Bugs Concerning Multilanguage | 4 | 5 | 5 | 0 | Walliser A.
Add id system to categorys | 7 | 5 | 5 | 0 | Walliser A.
Implemented change queue serverside | 4 | 4 | 4 | 0 | Wagner C.