## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
export isConected to a new Thread | 3 | 3 | 3 | 0 | Wagner C.
fix a bug that occours when two users add a item at the same time | 4 | 4 | 0 | 4 | Walliser A. / Wagner C.
make recipe description scrollable | 2 | 1 | 1 | 0 | Walliser A.
Hashing passwords | 1 | 2 | 2 | 0 | Wagner C.