## Tabelle1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Installing json-server | 1 | 1.5 | 0.5 | 1 | Wagner C.
Make post succesful requests to the server using postman | 3 | 3 | 0 | 3 | Wagner C.
replaceing current popup windows | 4 | 4 |  |  | Walliser A.
fixing ui design where the add button covers the last items of the list | 1 | 1 |  |  | Walliser A.