## Tabelle1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Installing json-server | 1 | 1.5 | 1 | 0 | Wagner C.
Make succesful post requests to the server using postman | 3 | 1.5 | 1.5 | 0 | Wagner C.
replaceing current popup windows | 4 | 4 | 4 | 0 | Walliser A.
fixing ui design where the add button covers the last items of the list | 1 | 1 | 1 | 0 | Walliser A.
Make json-server accesible for local network | 3 | 1 | 0.5 | 0 | Wagner C.
Fixng usability flaws concerning the expension of categorys | 3 | 4.5 | 3.5 | 1 | Walliser A.