## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Create docker image with database with database model | 6 | 9 | 9 | 0 | Wagner C.
Write config file with currently used shoppinglist | 1 | 1.5 | 1 | 0.5 | Wagner C.
Save multiple shoppinglists | 1 | 3 | 3 | 0 | Wagner C.
Extend Group feature(UI windows) | 3 | 6 | 3 | 3 | Walliser A.