## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Setup an application server which functions can be called from an Android client | 5 | 5 | 5 | 0 | C. Wagner
Make a login function for the application server | 3 | 3 | 2 | 1 | C. Wagner
Extend Group feature(UI windows) | 3 | 6 | 5.5 | 0 | Walliser A.
Make successful requests to application server | 3 | 3 | 3 | 0 | C. Wagner