## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
implement invitations backend | 4 | 5 | 5 | 0 | Wagner C.
Implement settings tab | 5 | 7 | 7 | 0 | Walliser A.