## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
finish group administration window | 3 | 2 | 2 | 0 | Walliser A.
impliment invitation tab | 3 | 3 | 3 | 0 | Walliser A.
Switch from json-server to nodejs server | 6 | 6 | 6 | 0 | Wagner C.
Change the way network operations are done to async | 2 | 4 | 4 | 0 | Wagner C.