## Tabellenblatt1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Implemented group synchronazition clientside | 10 | 14 | 14 | 0 | Wagner C.
Fixing Bugs Concerning Multilanguage | 2 | 2 | 2 | 0 | Walliser A.
Fixing Bugs (Connectinon and other) | 5 | 6 | 6 | 0 | Walliser A.
Adding Popups to alter group and and item List | 2 | 2 | 2 | 0 | Walliser A.