## Tabelle1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Fix UI bug: closing category "bought" when item removed | 2 | 4 | 2 | 2 | Walliser A.
Fixing Bugs in the Listview of the Shoppinglist | 6 | 6 | 0 | 6 | Walliser A.