## Tabelle1
Task | Orignal Estimate | Current Estimate | Effort | Remain | Responsible
Make a succesfull GET and POST request with the moblie | 4 | 4 | 0 | 4 | Wagner C.
Remove all bought items from the shoppinglist | 2 | 2 | 0 | 2 | Walliser A.
Fix UI bug: closing category "bought" when item removed | 2 | 2 | 0 | 2 | Walliser A.
Save items locally in json format | 4 | 4 | 3.5 | 0.5 | Wagner C.